## ToDoList
Category | Task | What | Who | When | Status | Details | Progress | Issues
Function | Scope definition |  |  |  | Started
Function | First batch choices
POC | Echo Localization | Check we can localize ApeRobot with SFR05 and logisitic regression | Jean | November 2015 | Started |  | work in progress
POC | Video via Raspberry | Check we can drive ApeRobot with Webcam over Internet | Jean | November 2015 | Canceled | At least feasible with Motion
POC | Motors speed control | Check we can control speed rotation with motors encoder |  |  | Ended | home made encoder / at the end work with analog read and asynchronous soft | at the end system reliable en term of distance | not that much precise regarding rotation
POC | Octave on Raspberry | Check we can use Octave on Raspberry to run logistic regresion |  |  | Canceled | Installation and first run Ok |  | raspberry to much power consuming
POC | Sound recognition | Check we can identify sound and sound direction |  | 2016
POC | Axis accelerometer | Check we can dectect ApeRobot orientation change |  |  | Ended | L3GD20H 3-Axis Gyro Carrier with voltage regulator | Tested: arduino connection and dialog >> decided to just use magnetometer as a first step
POC | Linear acceleromter
Integration | Raspberry | Check if we can use a raspberry as a network gateway and video system |  |  | Canceled |  |  | to much power consuming
POC | ESP8266 | Check if we can use a esp8266 as a network gateway and video system |  | december 2015 | Ended |  | Ok
Integration | Smartphone | Check if we can use a smartphone as a video system |  |  | Started | probably need to add a servo motor to rotate the camera
POC | Obstacle detection | Check if we can use echo to dynamicaly detect obstacles |  | january 2016 | Ended | need to work asynchronously | ok | to be design as an object
Integration | Power system | Choose power system |  |  | Started |  | it seams necessary to have 2 different power sources 1 for electronic and 1 for motors | encoders & echo system > permanent power consumption
POC | Integration Octave | determine the possibilities to integrate octave and java code |  |  | Ended |  | java defined as octave object
Development | Asynchronous communication | developp an asynchronous communication between Octave and Arduino using Java server
Development | Echo Localization | add northorientation to the learning data of the scans |  |  | canceled
Development | Echo Localization | developp a flat learning and use North Orientation to shift current scan according to flat measurment |  |  | Ended
Development | Define a global loop logic | Octave code |  |  | Started
Integration | Design an eletronic power switch | to reduce power consumption of encoders & echo system
Development | Check constitency between robot heading calculation and North Orientation |  |  |  | Started | octave loop
Development | Path determination | octave Astar code |  |  | Started
Development | Use mode pulse & NO to rotate little angle | arduino code
Development | Use NO to imporve rotation, precision | arduino code
Development | Use echo F B before and after move | to increase location precision
Development | Astar Path detemination | add possibility to inhibit some kind of move according to obastclea
Development | Use echo F B Right Left before rotation | to be sure to avoid osbacle
Development | Path Calculation add logic to take into account robot shape
Development | Octave developp a localization convergence loop | include robot move

## BOM
|  | Order | [5 empty] | Test |  |  | Robot components
What | For | When | Where | Status | PU | Qte | Total | When | Status | Rq | Selected | Qte | Cost
L3GD20 LSM303D BMP180 gyroscope accéléromètre boussole altimètre pour Arduino AL |  | 2015-10-21 | Ali | Received | 6.9 | 1 | 6.9 |  |  |  | Yes | 1 | 6.9
Voltage regulator TO-220 LT1085 CT-5 0 | power | 2015-10-14 | Ali | Received | 3.144 | 5 | 15.72 |  | Ok |  | Yes | 1 | 3.144
L7809CV 7809 Voltage Regulator IC TO-220 9 V 1.5A | power | 2015-10-28 | Ali | Received | 0.157 | 10 | 1.57 |  | pack of 10 pieces |  | Yes | 1 | 0.157
Motor 2342 L012CR 12 V 120 rpm avec codeur et boîte de vitesses |  | 2015-09-28 | Ali | Received | 14.68 | 2 | 29.36 | 2015-10-22 | encoder HS |  | Yes | 2 | 29.36
10x AA portable batterie Clip Holder Box Case |  | 2015-09-13 | Ali | Received | 1.28 | 2 | 2.56 | 2015-10-20 | Ok |  | Yes | 1 | 1.28
MG996R Micro Servo 180 | for echo localization 360 | 2015-09-10 | Ali | Received | 4.92 | 1 | 4.92 | 2015-09-30 | Ok |  | Yes | 1 | 4.92
IR emitter & receiver | for speed control | 2015-09-27 | Ali | Received | 0.1345 | 20 | 2.69 | 2015-10-22 | pack of 2x10 pieces |  | Yes | 2 | 0.269
Servo 360 grau Rotation continue Servo MG995 Metal Gear | for webcam 360 | 2015-08-27 | Ali | Received | 8.06 | 1 | 8.06 | 2015-09-30 | Ok | no reference position | Yes | 1 | 8.06
HC - SR05 echo | echo localization | 2015-08-27 | Ali | Received | 0.738 | 10 | 7.38 | 2015-10-01 | Ok |  | Yes | 4 | 2.952
Arduino Mega 2560 R3 Mega2560 REV3 |  | 2015-08-27 | Ali | Received | 5.38 | 2 | 10.76 | 2015-09-30 | Ok |  | Yes | 1 | 5.38
Dual bridge Motor driver L278M |  | 2015-08-27 | Ali | Received | 1.83 | 2 | 3.66 | 2015-10-01 | Ok |  | Yes | 1 | 1.83
L3GD20H |  |  | Ali | Received | 4.2 | 1 | 4.2 | 2015-10-15 | Ok |  | no | 0 | 0
Raspberry Pi 2 B |  | 2014 |  |  | 36 | 1 | 36 |  | Ok |  | no | 0 | 0
Wheel roues jaunes TAM6626J |  | 2014 | Gotronic | Received | 3.15 | 2 | 6.3 |  | Ok |  | Yes | 2 | 6.3
battery | power | [5 empty] | 0 |  |  |  |  | 1 | 0
buzzer |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 1 | 1
webcam | [6 empty] | 0 |  |  |  |  | 0 | 0
microphone | [6 empty] | 0 |  |  |  |  | 1 | 0
chain | transmission | 2015-11-23 | Tri Distribution | Received | 9 | 5 | 45 | 2015-11-27 | Ok | 1m used over 5m ordered | Yes | 1 | 9
pignions | transmission | 2015-11-24 | Tri Distribution | Received | 2 | 8 | 16 | 2015-11-28 | Ok |  | Yes | 6 | 12
FT232RL FTDI USB 3.3 V 5.5 V à TTL | communication | 2015-08-27 | Ali | Received | 1.71 | 1 | 1.71 | 2015-09-01 | Ok |  | Yes | 1 | 1.71
breadboard |  |  |  |  | 1 | 2 | 2 |  |  |  | Yes | 2 | 2
Rotation continue Servo MG995 360 | to rotate webcam | 2015-08-29 | Ali | Received | 8.06 | 1 | 8.06 | 2015-09-15 | Ok | no fixed point | no | 0 | 0
shaft | [6 empty] | 0 | [5 empty] | 0
Olimex ESP8266 |  |  | Imoex |  | 12 | 1 | 12 |  |  |  | yes | 1 | 12
resistors |  |  |  |  | 0.05 | [6 empty] | 12 | 0.6
LED |  |  |  |  | 0.05 | [5 empty] | yes | 5 | 0.25
Transistor |  |  |  |  | 0.1 | [6 empty] | 5 | 0.5
Zener diode |  |  |  |  | 0.5 | [6 empty] | 1 | 0.5
110.112
Note on B22: 5 Mètres Chaine Simple-ISO standard Au pas de : 6 (6 x 2,8 mm) 04-B1 1 Pignon Simple Pas 6 mm (04 1) Nbr de dents :9 PS04B09 2 Pignon Simple Pas 6 mm (04 1) Nbr de dents :10 PS04B10 2 Pignon Simple Pas 6 mm (04 1) Nbr de dents :12 PS04B12 2 Attache rapide pour chaine : 04B1 6 x 2,8 mm AR04B1 6 Pignon Simple Pas 6 mm (04 1) Nbr de dents :8 PS04B08 2

## Category
Architecture
Development
Function
Integration
Order
POC

## TestPlan
Basic function | Items | Progress | Precision | Result | Move precision
Scan | Once | 100% |  | ok
| Mutliple | 100% |  | ok
Move straightforward | Forward |  |  |  | 98%
Backward
Rotate | Clockwise
Counterclockwise
Align to North orientation | 0° alignement
angle
Detect obstacles | stop on back detection
stop on front detection
restart after obstacle disappearance
Determine North Orientation
Determine Localization | Case north oriented
Case not north oriented
Compute trajectory | Determine global trajectory
Alimentation | Monitor voltage
Wheel control

## MoveTest
Request |  |  |  | Computed |  | Real |  |  | North Orientation | [5 empty] | refNO a 1m | 126 | refNO a 0 | 138
Distance | Rotation | PosX |  | PosY | ComputedRotation | Distance Left | Distance Right | RealRotation | Before | Alter | Delta NO | DeltaNOVsRef | DeltaCompReal | DeltaNOReal | TrigoPosXY
100 | 0 | 96 | 96.0469 | -3 | 3 | 100 | 104 | 5 | 138 | 123 | 15 | 3 | -2 | 10 | -1.7899
100 | 0 | 97 | 97.0206 | 2 | 6 | 101.5 | 104.5 | 3 | 138 | 124 | 14 | 2 | 3 | 11 | 1.1812
100 | 0 | 96 | 96.1301 | 5 | 9 | 102 | 104.5 | 5 | 138 | 124 | 14 | 2 | 4 | 9 | 2.9815
100 | 0 | 97 | 97.0052 | 1 | 6 | 100 | 103 | 5 | 138 | 123 | 15 | 3 | 1 | 10 | 0.59066
100 | 0 | 95 | 95.0474 | 3 | 12 | 99.5 | 103.5 | 6 | 138 | 123 | 15 | 3 | 6 | 9 | 1.8087
100 | 0 | 97 | 97.0464 | 3 | 6 | 98 | 102.5 | 7 | 138 | 121 | 17 | 5 | -1 | 10 | 1.7715
100 | 0 | 96 | 96.0833 | 4 | 9 | 99 | 103 | 5 | 138 | 121 | 17 | 5 | 4 | 12 | 2.3859
100 | 0 | 97 | 97.0824 | 4 | 6 | 98.5 | 102.5 | 6 | 138 | 121 | 17 | 5 | 0 | 11 | 2.3614
-100 | 0 | -99 | 99.0202 | -2 | 3 | 101.5 | 99.8 | 3 | 126 | 134 | -8 | 4 | 0 | -11 | 1.1573
100 | 0 | 99 | 99 | 0 | 3 | 100.5 | 99.7 | -1 | 138 | 127 | 11 | -1 | 4 | 12 | 0
-100 | 0 | -99 | 99.0202 | -2 | 3 | 103 | 102 | 1 | 126 | 136 | -10 | 2 | 2 | -11 | 1.1573
100 | 0 | 95 | 95.0211 | 2 | 12 | 99 | 99.5 | 0.5 | 138 | 125 | 13 | 1 | 11.5 | 12.5 | 1.206
-100 | 0 | -99 | 99.0051 | 1 | -3 | 101.2 | 104 | -4 | 126 | 139 | -13 | -1 | 1 | -9 | -0.57873
100 | 0 | 94 | 94.2603 | 7 | 12 | 99.5 | 99 | -1 | 138 | 126 | 12 | 0 | 13 | 13 | 4.2588
-100 | 0 | -99 | 99 | 0 | 3 | 101.2 | 101.5 | 0 | 126 | 137 | -11 | 1 | 3 | -11 | 0
100 | 0 | 93 | 93.086 | 4 | 9 | 101 | 99 | -3 | 138 | 128 | 10 | -2 | 12 | 13 | 2.4628
-100 | 0 | -99 | 99 | 0 | 3 | 102.5 | 101.5 | 0.5 | 126 | 136 | -10 | 2 | 2.5 | -10.5 | 0
100 | 0 | 95 | 95.1893 | 6 | 12 | 99.4 | 99 | 1 | 138 | 126 | 12 | 0 | 11 | 11 | 3.6139
-100 | 0 | -99 | 99.0454 | -3 | 3 | 98.8 | 100 | -3 | 126 | 138 | -12 | 0 | 6 | -9 | 1.7357
100 | 0 | 99 | 99 | 0 | 3 | 102.5 | 101.5 | -0.5 | 138 | 127 | 11 | -1 | 3.5 | 11.5 | 0
-100 | 0 | -99 | 99.0051 | -1 | 3 | 101 | 98.5 | 2 | 126 | 133 | -7 | 5 | 1 | -9 | 0.57873
-100 | 0 | -99 | 99.1262 | -5 | 3 | 101.7 | 101 | 0 | 126 | 136 | -10 | 2 | 3 | -10 | 2.8913
100 | 0 | 99 | 99.0202 | -2 | -3 | 101 | 98.5 | -4 | 138 | 129 | 9 | -3 | 1 | 13 | -1.1573
100 | 0 | 97 | 97.0464 | -3 | -6 | 99.5 | 98.5 | -5 | 138 | 129 | 9 | -3 | -1 | 14 | -1.7715
-100 | 0 | -97 | 97.1854 | -6 | 9 | 101 | 100.5 | 0 | 126 | 136 | -10 | 2 | 9 | -10 | 3.5396
100 | 0 | 99 | 99 | 0 | 3 | 100.5 | 100 | -0.5 | 138 | 136 | 2 | -10 | 3.5 | 2.5 | 0
-100 | 0 | -97 | 97 | 0 | 6 | 100.2 | 97.5 | 3 | 126 | 134 | -8 | 4 | 3 | -11 | 0
100 | 0 | 97 | 97.0824 | 4 | 6 | 98 | 100.5 | 2 | 160 | 145 | 15 | -19 | 4 | 13 | 2.3614
-100 | 0 | -99 | 99.0808 | -4 | 3 | 105 | 102.5 | 4 | 145 | 159 | -14 | -21 | -1 | -18 | 2.3137
100 | 0 | 96 | 96.3328 | 8 | 9 | 99 | 103 | 6 | 160 | 143 | 17 | -17 | 3 | 11 | 4.7636
-100 | 0 | -99 | 99.0051 | 1 | 3 | 103 | 99 | 5 | 145 | 159 | -14 | -21 | -2 | -19 | -0.57873
100 | 0 | 96 | 96.1301 | 5 | 9 | 99 | 101.5 | 2.5 | 136 | 124 | 12 | 2 | 6.5 | 9.5 | 2.9815
-100 | 0 | 99 | 99.0202 | -2 | 3 | 98 | 102 | 5 | 126 | 133 | -7 | 5 | -2 | -12 | -1.1573
100 | 0 | 93 | 93.4345 | 9 | 15 | 97 | 103 | 7 | 136 | 119 | 17 | 7 | 8 | 10 | 5.5275
-100 | 0 | -99 | 99.0051 | -1 | 3 | 102.5 | 101 | 1 | 119 | 135 | -16 | 3 | 2 | -17 | 0.57873
-100 | 0 | -96 | 96.0052 | 1 | -3 | 105 | 0 | -7 | 127 | 144 | -17 | -6 | 4 | -10 | -0.59681
100 | 0 | 97 | 97 | 0 | 0 | 99.5 | 102.5 | 5 | 144 | 124 | 20 | 2 | -5 | 15 | 0
-100 | 0 | -96 | 96.0208 | 2 | -3 | 95 | 100 | -7 | 124 | 146 | -22 | -8 | 4 | -15 | -1.1935
100 | 0 | 93 | 93.0484 | 3 | 15 | 99.5 | 101.5 | 2 | 138 | 124 | 14 | 2 | 13 | 12 | 1.8476
-100 | 0 | -99 | 99 | -1 | 3 | 99.5 | 98 | -1 | 126 | 141 | -15 |  | 4 | -14 | 0.57873
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on B26: modif delay check poisition 200 vs250
Note on B30: modif delay check poisition 300 vs250
Note on B34: modif delay check poisition250