## ToDoList
Category | Task | What | Who | When | Status | Details | Progress | Issues
Function | Scope definition |  |  |  | Started
Function | First batch choices
POC | Echo Localization | Check we can localize ApeRobot with SFR05 and logisitic regression | Jean | November 2015 | Started
POC | Video via Raspberry | Check we can drive ApeRobot with Webcam over Internet | Jean | November 2015 | Started | At least feasible with Motion
POC | Motors speed control | Check we can control speed rotation with motors encoder | [5 empty] | 1 encoder HS signal need to be amplify
POC | Octave on Raspberry | Check we can use Octave on Raspberry to run logistic regresion |  |  | Started | Installation and first run Ok
POC | Sound recognition | Check we can identify sound and sound direction |  | 2016
POC | Axis accelerometer | Check we can dectect ApeRobot orientation change |  |  | Started | L3GD20H 3-Axis Gyro Carrier with voltage regulator | Tested: arduino connection and dialog
POC | Linear acceleromter

## BOM
|  | Order | [5 empty] | Test |  |  | Robot components
What | For | When | Where | Status | PU | Qte | Total | When | Status | Rq | Selected | Qte | Cost
L3GD20 LSM303D BMP180 gyroscope accéléromètre boussole altimètre pour Arduino AL |  | 2015-10-21 | Ali | Received | 6.9 | 1 | 6.9 | [5 empty] | 0
Voltage regulator TO-220 LT1085 CT-5 0 | power | 2015-10-14 | Ali | Received | 3.144 | 5 | 15.72 |  | Ok |  | Yes | 1 | 3.144
L7809CV 7809 Voltage Regulator IC TO-220 9 V 1.5A | power | 2015-10-28 | Ali | Received | 0.157 | 10 | 1.57 |  | pack of 10 pieces |  | Yes | 1 | 0.157
Motor 2342 L012CR 12 V 120 rpm avec codeur et boîte de vitesses |  | 2015-09-28 | Ali | Received | 14.68 | 2 | 29.36 | 2015-10-22 | encoder HS |  | Yes | 2 | 29.36
10x AA portable batterie Clip Holder Box Case |  | 2015-09-13 | Ali | Received | 1.28 | 2 | 2.56 | 2015-10-20 | Ok |  |  |  | 0
MG996R Micro Servo 180 | for echo localization 360 | 2015-09-10 | Ali | Received | 4.92 | 1 | 4.92 | 2015-09-30 | Ok |  | Yes | 1 | 4.92
IR emitter & receiver | for speed control | 2015-09-27 | Ali | Received | 0.1345 | 20 | 2.69 | 2015-10-22 | pack of 2x10 pieces |  | Yes | 2 | 0.269
Servo 360 grau Rotation continue Servo MG995 Metal Gear | for webcam 360 | 2015-08-27 | Ali | Received | 8.06 | 1 | 8.06 | 2015-09-30 | Ok | no reference position | Yes | 1 | 8.06
HC - SR05 echo | echo localization | 2015-08-27 | Ali | Received | 0.738 | 10 | 7.38 | 2015-10-01 | Ok |  | Yes | 4 | 2.952
Arduino Mega 2560 R3 Mega2560 REV3 |  | 2015-08-27 | Ali | Received | 5.38 | 2 | 10.76 | 2015-09-30 | Ok |  | Yes | 1 | 5.38
Dual bridge Motor driver L278M |  | 2015-08-27 | Ali | Received | 1.83 | 2 | 3.66 | 2015-10-01 | Ok |  | Yes | 1 | 1.83
L3GD20H |  |  | Ali | Received | 4.2 | 1 | 4.2 | 2015-10-15 | Ok |  |  |  | 0
Raspberry Pi 2 B |  | 2014 |  |  | 36 | 1 | 36 |  | Ok |  | Yes | 1 | 36
Wheel roues jaunes TAM6626J |  | 2014 | Gotronic | Received | 3.15 | 2 | 6.3 |  | Ok |  | Yes | 2 | 6.3
battery | power | [5 empty] | 0 |  |  |  |  | 1 | 0
buzzer | [6 empty] | 0 |  |  |  |  | 1 | 0
webcam | [6 empty] | 0 |  |  |  |  | 1 | 0
microphone | [6 empty] | 0 |  |  |  |  | 1 | 0
chain | transmission | 2015-11-23 | Tri Distribution | Received | 9 | 5 | 45 | 2015-11-27 | Ok | 1m used over 5m ordered | Yes | 1 | 9
pignions | transmission | 2015-11-24 | Tri Distribution | Received | 2 | 8 | 16 | 2015-11-28 | Ok |  | Yes | 6 | 12
FT232RL FTDI USB 3.3 V 5.5 V à TTL | communication | 2015-08-27 | Ali | Received | 1.71 | 1 | 1.71 | 2015-09-01 | Ok |  | Yes | 1 | 1.71
breadboard |  |  |  |  | 1 | 2 | 2 |  |  |  | Yes | 2 | 2
Rotation continue Servo MG995 360 | to rotate webcam | 2015-08-29 | Ali | Received | 8.06 | 1 | 8.06 | 2015-09-15 | Ok | no fixed point |  |  | 0
0
0
resistors | [12 empty] | 0
123.082
Note on B22: 5 Mètres Chaine Simple-ISO standard Au pas de : 6 (6 x 2,8 mm) 04-B1 1 Pignon Simple Pas 6 mm (04 1) Nbr de dents :9 PS04B09 2 Pignon Simple Pas 6 mm (04 1) Nbr de dents :10 PS04B10 2 Pignon Simple Pas 6 mm (04 1) Nbr de dents :12 PS04B12 2 Attache rapide pour chaine : 04B1 6 x 2,8 mm AR04B1 6 Pignon Simple Pas 6 mm (04 1) Nbr de dents :8 PS04B08 2

## Category
Architecture
Development
Function
Integration
Order
POC