## ToDoList
Category | Task | What | Who | When | Status | Details | Issues
Function | Scope definition |  |  |  | Started
Function | First batch choices
POC | Echo Localization | Check we can localize ApeRobot with SFR05 and logisitic regression | Jean | November 2015 | Started
POC | Video via Raspberry | Check we can drive ApeRobot with Webcam over Internet | Jean | November 2015 | Started | At least feasible with Motion
POC | Motors speed control | Check we can control speed rotation with motors encoder |  |  |  |  | 1 encoder HS signal need to be amplify
POC | Octave on Raspberry | Check we can use Octave on Raspberry to run logistic regresion |  |  | Started | Installation and first run Ok
POC | Sound recognition | Check we can identify sound and sound direction |  | 2016

## Category
Architecture
Development
Function
Integration
Order
POC